## Sheet1
Individual Project
Name: Jiaqi Yao |  |  | Start Date: 30th January 2024 | [60 empty] | *
Project Lead: Dong Wang |  |  | End of Tasks before 20th March 2024 |  | W/C 30th Jan | [6 empty] | W/C 6th Feb | [6 empty] | W/C 13th Feb | [6 empty] | W/C 20th Feb | [6 empty] | W/C 27th Feb | [6 empty] | W/C 6th March | [6 empty] | W/C 13th March | [6 empty] | W/C 20th March | [6 empty] | 27th-30th
Task | Duration | Start Date | End Date | Collaboration | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Data Collection with Dr. Changhong and Dr. Xinyue | 10 days | 15/01/24 | 24/01/24 | Dr. Changhong, Dr. Xinyue | bar: W/C 30th Jan 30
Review Data Accuracy and Usability | 3 days | 25/01/24 | 27/01/24 | Dr. Changhong, Dr. Xinyue | bar: W/C 30th Jan 31 to W/C 30th Jan 1
Initial Model Development | 7 days | 29/01/24 | 2024-04-02 | bar: W/C 30th Jan 2 to W/C 30th Jan 4
Model Refinement Discussion with Dr. Dongwang | 1 day | 2024-05-02 | 2024-05-02 | Dr. Dongwang | bar: W/C 30th Jan 5 to W/C 6th Feb 10
Implementation of Model Improvements | 5 days | 2024-06-02 | 2024-12-02 | bar: W/C 30th Jan 5
Evaluation of Model Accuracy and Efficiency | 3 days | 13/02/24 | 16/02/24 | Dr. Dongwang | bar: W/C 6th Feb 6
Finalization of Model Adjustments | 2 days | 19/02/24 | 20/02/24 | Dr. Dongwang | bar: W/C 6th Feb 7
Prototype Testing and Iteration | 14 days | 21/02/24 | 2024-08-03 | Dr. Dongwang | bar: W/C 6th Feb 8
Final Review with Dr. Dongwang | 1 day | 2024-09-03 | 2024-09-03 | Dr. Dongwang | bar: W/C 6th Feb 9
Optimization for Real-time Application | 10 days | 2024-10-03 | 21/03/24 | bar: W/C 6th Feb 10
Comprehensive Testing and Validation | 20 days | 22/03/24 | 19/04/24 | bar: W/C 30th Jan 2 to W/C 6th Feb 6
Feedback Integration and Final Adjustments | 5 days | 20/04/24 | 25/04/24 | Dr. Dongwang | bar: W/C 30th Jan 2
Project Report Draft | 5 days | 26/04/24 | 2024-02-05 | bar: W/C 30th Jan 3
Final Report and Documentation | 5 days | 2024-03-05 | 2024-09-05 | bar: W/C 30th Jan 4
Project Closure Meeting | 1 day | 2024-10-05 | 2024-10-05 | All Stakeholders | bar: W/C 30th Jan 5